## Malad
Saimita
Sno | Date | Invoice Number | Total | Payment | Site name | Approved | Remaining | Remark
1 | 2024-01-30 | BF/0124/055 | 189726 | 151781 | Prabhu plaza | 151781 | 37945 | 20% hold
2 | 2024-02-29 | NBF/0224/053 | 151270 | 121016 | Prabhu plaza | 121016 | 30254 | 20% hold
3 | 2024-03-30 | NBF/0324/052 | 181100 |  | Prabhu plaza | 144880 | 36220
4
5
6
7
8
9
10
11
12
13
14
522096

## Borivali
Saimita
Sno | Date | Invoice Number | Total | Payment | Site name | Approved 80% | Remaining | Remark
1 | 2023-12-21 | NBF/1223/052 | 30000 | 30000 | Punit kurla |  | 0
2 | 2023-12-31 | NBF/1223/054 | 51000 | 51000 | Rodium |  | 0 | done
3 | 2023-12-31 | NBF/1223/055 | 30890 |  | Punit kurla |  |  | Menpower
4 | 31/12/2023 | NBF/0124/051 | 70776 | 56621 | Borivali singnate |  | 14155 | 20% hold | done
5 | 2024-01-29 | NBF/0124/053 | 129861 | 103889 | Borivali singnate | 103889 | 25972 | 20% hold | done
6 | 2024-01-30 | BF/0124/055 | 189726 | 151781 | Prabhu plaza | 151781 | 37945 | 20% hold
7 | 2024-02-29 | NBF/0224/053 | 151270 | 120000 | Prabhu plaza | 121016 | 30254 | 20% hold and 1016 pending
| 2024-02-29 | NBF/0224/054 | 100581 |  | Borivali singnate not submit
8 | 2024-03-30 | NBF/0324/053 | 72789 | 58231 | Borivali singnate | 58231 | 14557 | 20% hold | done
9 | 2024-03-30 | NBF/0324/052 | 181100 | 116769 | Prabhu plaza | 144880 | 36220 | 20% hold + 28111
10 | 2024-05-03 | NBF/0524/051 | 123950 |  | Prabhu plaza | 99160 | 24970 | 20% hold
11 | 2024-05-23 | NBF/0524/052 | 146736 |  | Borivali singnate | 115000 | 29347.2 | 20% hold +2389 | done
12 | 2024-05-25 | NBF/0524/053 | 142675 |  | Prabhu plaza | 12000 |  | Rework and payment final
13 | 2024-06-07 | NBF/0524/054 | 129209 |  | Prabhu plaza | 129209 |  | 20 % malad holding
14 | 2024-06-28 | NBF/0624/14 | 120097 |  | Borivali singnate |  |  |  | done
15 | 2024-08-30 | NBF/0824/15 | 186300 |  | Mehta | 150000 | 37360
16 | 2024-09-30 | NBF/0924/16 | 127480 |  | Borivali singnate | 101984 | 25496 |  | done
17 | 2024-09-30 | NBF/0924/17 | 350063 |  | Rashmi Celestia | 280050 | 70013 | final
18 | 2024-09-30 | NBF/0924/18 | 131168 |  | Mehta | 104934.4 | 26233.6
| 2024-11-27 | NBF/0924/19 | 87613 |  | Rashmi Celestia
| 29/11/2024 | NBF/0924/020 | 34882 |  | Mehta (Vorivali west)
| 29/11/2024 | NBF/0924/021 | 31500 |  | Vashudev (Vorivali west)
| 30/12/2024 | NBF/1224/022 | 77379.6 |  | Mehta
| 30/12/2024 | NBF/1224/023 | 206593 |  | Prity CHSL (Ghatcopar)
| 30/12/2024 | NBF/1224/24 | 63750 |  | Rashmi Celestia
| 30/12/2024 | NBF/1224/25 | 146131 |  | Borivali singnate
| Total |  | 3113519.6 | 688291 |  | 1572134.4
129861
189726
151270
100581
72789
|  | 10000 | [6 empty] | 181100
| 17/06/2024 | 10000 | [6 empty] | 123950
|  | 30000 | [6 empty] | 146736
142675
129209
120097
186300
127480
350063
131168
87613
34882
31500
2437000

## Sheet1
Total payment basant
Sr. No | Date | Amount | mode | remark

## Sheet2
| Mehta |  |  |  |  | 100 | 150 | 80
Sr.no | Description | Quantity | Rate | Amount (Rs.) |  | 7 | 30 | 5
1 | 100 mm ring-line | 125.1 mtr | 400 | 50040 |  | 2 | 10
2 | 80 mm hydrant post | 3.25 mtr | 300 | 975 | 2500 | 2.3 | 4
3 | 150 mm pipe | 21.6 mtr | 600 | 12960 | 2500 | 27 | 5
4 | pump-room work completed |  |  | 100000 | 5000 | 4.9
5 | flexodroup | 8 nos | 100 | 800 | 10000 | 43.2 | 49
6 | 4 inch NRV | 1 nos | 360 | 360 | 4000
7 | 4 inch butter-fly | 1 nos | 360 | 360 | 24000
|  | Total |  | 165495
|  | Advance |  | 0
|  | To be Paid |  | 165495
| Borivali DG SIngnate |  |  |  | 11
Sr.no | Description | Quantity | Rate | Amount (Rs.) | 3
1 | 1st floor sprinkler line completed | 17 nos | 700 | 11900 | 11
2 | 50 mm dancher line | 37 mtr | 220 | 8140 | 3
3 | 25 mm QD line | 37 mtr | 110 | 4070 | 9
4 | 150 mm sprinkler riser | 69 mtr | 600 | 41400 | 37
5 | 150 mm hydrant riser | 69 mtr | 600 | 41400 |  | 127605
6 | 25 mm drain line | 70 mtr | 110 | 7700
7 | 50 mm 18th floor dancher line | 12 mtr | 220 | 2640
|  | Total |  | 117250
|  | Advance |  | 0
|  | To be Paid |  | 117250
Celestia
Sr.no | Description | Quantity | Rate | Amount (Rs.)
1 | 25 mm pipe | 35.1 mtr | 110 | 3860
2 | 80 mm pipe | 13.2 mtr | 300 | 3960
3 | 100 mm pipe | 127.3 mtr | 400 | 50920
4 | 150 mm pipe | 101.1 mtr | 600 | 60660
5 | Singal Hydrant valve | 5 nos | 200 | 1000
6 | double hydrant valve | 3 nos | 300 | 900
7 | Hose-Reel drum | 3 nos | 450 | 1350
8 | 6 inch butter-fly | 1 nos | 540 | 540
9 | 6 inch NRV | 1 nos | 540 | 540
10 | pump room complete installation | 1 nos |  | 100000
11 | ground floor residential area flex-valve fitting | 21 nos | 100 | 2100
12 | 1st floor residential area flexi-valve fitting | 21 nos | 100 | 2100
13 | Ground floor sprinkler point | 63 nos | 750 | 47250
14 | 1st floor sprinkler point | 36 nos | 750 | 27000
15 | 2st floor sprinkler point | 36 nos | 750 | 27000
16 | 3st floor sprinkler point | 36 nos | 750 | 27000
|  | Total |  | 356180
|  | Advance |  | 0
|  | To be Paid |  | 356180
Sr.no | Description | Quantity | Rate | Amount (Rs.)
1 | NBF/0924/17 20% holding |  |  | 70013
2 | 150 mm ringline | 24 mtr | 600 | 14000
3 | 100 mm ringline | 9 mtr | 400 | 3600
4 | 80 mm Hydrant post | 6.1 mtr | 300 | 1830
|  | Total |  | 87613
|  | Advance |  | 0
|  | To be Paid |  | 87613
30/12/2024
Mehta final
Sr.no | Description | Quantity | Rate | Amount (Rs.)
1 | NBF/0824/15 20% holding |  |  | 37360
2 | NBF/0924/18 20% holding |  |  | 26233.6
3 | NBF/0924/20 20% holding |  |  | 4286
4 | Singal Hydrant valve | 4 nos | 200 | 800
5 | Dual Hydrant valve | 5 nos | 300 | 1500
6 | two way inlet installation | 2 nos | 300 | 600
7 | Hose-pipe installation | 4 nos | 50 | 200
8 | Short branch pipe | 4 nos | 50 | 200
9 | Hose-Reel drum installation | 5 nos | 400 | 2000
10 | Hose-box installation double door | 4 nos | 200 | 800
11 | Flex-valve drum with rosser plate installation | 10 nos | 100 | 1000
12 | Sprinkler point extention | 6 nos | 100 | 600
13 | Ms angle and channel | 70 kg | 15 | 1050
14 | fire Extinguishers installation | 9 | 50 | 450
15 | fire buckets installation | 6 | 50 | 300
| Note : All floor testing completed | Total |  | 77379.6
|  | Advance |  | 0
|  | To be Paid |  | 77379.6
Ghatkopar | Priti chsl
Sr.no | Description | Quantity | Rate | Amount (Rs.)
1 | Pumproom installation |  |  | 100000
2 | Hose-Reel drum installation | 11 nos | 400 | 44000
3 | two way inlet installation | 2 nos | 300 | 600
4 | Singal hydrant valve installation | 2 nos | 200 | 400
5 | double hydrant valve installation | 11 nos | 300 | 3300
6 | 100 mm tank inlet ringline installation | 28.7 mtr | 360 | 10332
7 | 100 mm tank inlet ringline wrapping-coating | 27 mtr | 15 | 405
8 | 150 mm ringline to raiser to pumproom connection installation | 45.8 mtr | 540 | 24732
9 | 150 mm ringline to raiser to pumproom connection wrapping-coating | 40 mtr | 15 | 600
10 | 100 mm pipe sprinkler raiser to pumproom connection installation | 15.8 mtr | 360 | 5688
11 | 100 mm pipe sprinkler raiser to pumproom connection wrapping-coating | 13.8 mtr | 15 | 207
12 | 80 mm hydrant post and drain line installation | 13.8 mtr | 300 | 4140
13 | 80 mm hydrant post and drain line wrapping-coating | 10 mtr | 15 | 150
14 | 200 mm pipe fire tank to pumproom installation | 15.4 mtr | 720 | 11088
15 | 200 mm pipe fire tank to pumproom wrapping-coating | 15.4 mtr | 15 | 231
16 | 100 mm butterfly installation | 1 nos | 360 | 360
17 | 10 mm NRV installation | 1 nos | 360 | 360
|  | Total |  | 206593
|  | Advance |  | 0
|  | To be Paid |  | 206593
DG signate
Sr.no | Description | Quantity | Rate | Amount (Rs.)
1 | Pumproom installation |  |  | 100000
2 | Ground floor sprinkler point | 17 nos | 750 | 12750
3 | 150 mm pipe Raiser to pump-room connection sprinkler line | 11.4 mtr | 600 | 6840
4 | 150 mm hydrant raiser to pump room connection | 10.6 mtr | 600 | 6360
5 | 25 mm drain line | 12.1 mtr | 110 | 1331
6 | 1st floor to 19th floor sprinkler fitting completed | 377 nos | 50 | 18850
|  | Total |  | 146131
|  | Advance |  | 0
|  | To be Paid |  | 146131
Celesiti
Sr.no | Description | Quantity | Rate | Amount (Rs.)
1 | 5th floor CPVC Sprinkler point | 23 | 650 | 14950
2 | 5th floor passage sprinkler point | 9 | 700 | 6300
3 | 6th floor CPVC Sprinkler point | 23 | 650 | 14950
4 | 6th floor passage sprinkler point | 9 | 700 | 6300
5 | 7th floor CPVC Sprinkler point | 23 | 650 | 14950
6 | 7th floor passage sprinkler point | 9 | 700 | 6300
|  | Total |  | 63750
|  | Advance |  | 0
|  | To be Paid |  | 63750