## Sheet1
Total Payment log |  |  |  |  | Fire Infra Floor sprinkler work
Date | payment | Date | Bill | Remark | Date | payment | Remark

## Sheet2
Sr.no | Description | Quantity | Rate | Amount (Rs.)
1 | 6th floor Sprinkler line installation and testing done | 1 | 80,000.00/NOS | 80000
2 | 7th floor Sprinkler line installation and testing done | 1 | 80,000.00/NOS | 80000
3 | 9th floor Sprinkler line installation and testing done | 1 | 80,000.00/NOS | 80000
4 | 10th floor Sprinkler line installation and testing done | 1 | 80,000.00/NOS | 80000
5 | 11th floor Sprinkler line installation and testing done | 1 | 80,000.00/NOS | 80000
6 | 14th floor Sprinkler line installation and testing done | 1 | 80,000.00/NOS | 80000
7 | 15th floor Sprinkler line installation and testing done | 1 | 80,000.00/NOS | 80000
8 | 16th floor Sprinkler line installation and testing done | 1 | 80,000.00/NOS | 80000
9 | 17th floor Sprinkler line installation and testing done | 1 | 80,000.00/NOS | 80000
10 | 18th floor Sprinkler line installation and testing done | 1 | 80,000.00/NOS | 80000
|  | Total |  | 800000
|  | Advance |  | 540000
|  | To be Paid |  | 260000